## Sheet1
SIP_ID | Improvement_Area | Current_Status | Goal | Action_Plan | Responsible_Person | Start_Date | End_Date | Progress_Status | KPIs | Stakeholders | Risks_and_Mitigation | Review_Date | Notes
SIP-2025-001 | Ticket Resolution Time | Avg. resolution time: 48 hrs | Reduce to 38 hrs (20% reduction) | Implement automated ticket routing and escalation | John Smith | 2025-05-01 | 2025-06-15 | Not Started | Avg. resolution time, # escalations | IT, Service Desk, Users | Staff resistance to new process; provide training | 2025-06-20 | Pilot in one department
SIP-2025-002 | Self-Service Portal Usage | 25% of Tier 1 issues resolved via portal | Increase to 40% | Deploy AI chatbot and update knowledge base | Priya Patel | 2025-05-05 | 2025-07-01 | In Progress | Self-service rate, CSAT | IT, End Users, HR | Low adoption; run awareness campaign | 2025-07-10 | Monitor feedback weekly
SIP-2025-003 | Automation of Password Reset | 10 hrs/week spent on manual resets | Automate 80% of resets (save 8 hrs/wk) | Implement password reset automation tool | Alex Chen | 2025-05-10 | 2025-06-10 | Not Started | Time saved, # auto resets | IT, Security | Integration issues; test in dev environment | 2025-06-15 | Vendor support available